## Master
S.No. | Sheet
1 | LOE
2 | Plan
3 | Infra Architecture
4 | Branching Strategy for Infra
5 | Control Flow for Infra
6 | Branching Strategy for DevOps
7 | Pipeline Architecture - DevOps
8 | Control Flow
9 | Escalation Access Matrix
10 | Understanding
11 | Business Understanding
12 | Moving Components
13 | Cost Estimation
14 | Naming Conversion
15 | Doc Plan
16 | Azure AD B2C Tenant Pricing
17 | SOP
18 | Ref

## LOE
S.No | Work items | SDM | LEAD | ENGINEER | Planned hours
Define
1 | Kickoff Deck | 2 |  |  | 2
2 | Defining Prep work |  | 2 | 2 | 4
3 | Defining Permission levels (level of access) | 1 |  |  | 1
4 | Defining Contact and availability Matrix | 1 |  |  | 1
5 | Understanding of the Business | 1 | 1 | 1 | 3
6 | Defining Stakeholders and our end goal | 1 |  |  | 1
7 | Planning and listing the tasks in Taiga |  | 1 |  | 1
8 | Defining the moving components |  |  | 1 | 1
Design
9 | Architecture Diagram |  |  | 2 | 2
10 | Planning the SKUs, Configuration and Network setup |  | 1 | 2 | 3
11 | Cost Estimation |  |  | 1 | 1
12 | Design the branching strategy |  | 1 | 1 | 2
13 | Design Pipeline strategy |  | 1 | 1 | 2
14 | Designing project structure, Tasks and boards, SCM, Build dependencies, Releasing Artifacts, CI/CD Pipelines |  |  | 1 | 1
15 | Designing the Implementation roadmap (Contains infrastructure Architecture, DevOps architecture, Application Architecture) |  | 1 |  | 1
Develop
16 | POC for creating resources using arm templates |  | 2 |  | 2
17 | Access for Azure Portal, Azure DevOps, Creating Project and Repos in DevOps, Branching Strategy |  |  | 1 | 1
18 | Creating ARM Templates, Blueprint files, Assignment Files |  | 2 |  | 2
19 | Validate the Blueprint and Assignment Files |  | 2 |  | 2
Deploy
20 | Setup CI/CD pipeline for infrastructure deployment |  | 1 | 1 | 2
21 | Executing CI/CD pipeline and to verify the resources deployed and troubleshooting errors if any | 1 | 1 | 1 | 3
22 | Pushing Source code from local repo to Azure Repo |  |  | 1 | 1
23 | Setup CI/CD pipeline for Front End |  |  | 1 | 1
24 | Setup CI/CD pipeline for Back End |  |  | 1 | 1
25 | Executing CI/CD pipeline for Front & Back End and troubleshooting errors if any | 1 | 1 | 1 | 3
26 | Custom Domain and SSL | 1 | 1 | 1 | 3
Documentation
28 | Documentation |  | 1 | 2 | 3
29 | Application and environment monitoring |  | 1 | 1 | 2
Total |  | 9 | 20 | 23 | 52

## Plan
S.No | Tasks / Work items | Resource | ETA | Status | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20
Phase 1 : Assessment
1 | Kickoff Deck | Megha | 2022-06-06 | Completed
2 | Business Understanding | Bala/Swetha | 2022-06-06 | Completed
3 | LOE | Bala/Swetha | 2022-06-06 | Completed
4 | Project Plan | Bala/Swetha | 2022-06-06 | Completed
3 | Defining Prep work | Bala/Swetha | 2022-06-07 | Completed
5 | Defining Contact and availability Matrix | Bala | 2022-06-07 | Completed
Phase 2 : Architecture & Planning
6 | Defining the moving components in Application | Bala | 2022-06-08 | Completed
7 | Architecture Diagram | Bala | 2022-06-08 | Completed
8 | Planning the SKUs, Configuration and Network setup | Bala/Swetha | 2022-06-09 | Completed
9 | Cost Estimation | Bala | 2022-06-09 | Completed
10 | Defining the branching strategy | Swetha | 2022-06-07 | Completed
11 | Defining Pipeline strategy | Swetha | 2022-06-07 | Completed
12 | Planning project structure, SCM, Build dependencies, Releasing Artifacts, CI/CD Pipelines | Bala/Swetha | 2022-06-07 | Completed
13 | Defining the Implementation roadmap( Contains infrastructure Architecture, DevOps architecture, Application Architecture) | Bala | 2022-06-10 | Completed
14 | Finalizing DevOps strategy | Bala/Swetha | 2022-06-11 | Completed
15 | Reviewing architectural design | Megha/Bala/Swetha | 2022-06-12 | Completed
16 | Define Project kick-off presentation | Megha | 2022-06-13 | Completed
Phase 3 : Implementation of Core Services
17 | Access for Azure Portal, Azure DevOps, Creating Project and Repos in DevOps, Branching Strategy | Bala | 2022-06-11 | Completed
18 | Creating ARM Templates, Blueprint files, Assignment Files | Swetha | 2022-06-13 | Completed
19 | Validate the Blueprint and Assignment Files | Swetha | 2022-06-13 | Completed
20 | Setup CI/CD pipeline for infrastructure deployment | Swetha | 2022-06-14 | Completed
21 | Executing CI/CD pipeline and to verify the resources deployed | Swetha | 2022-06-14 | Completed
22 | Pushing Source code from local repo to Azure Repo | Bala | 2022-06-14 | Completed
23 | Setup CI/CD pipeline for Front End | Bala | 2022-06-14 | Completed
24 | Setup CI/CD pipeline for Back End | Bala | 2022-06-14 | Completed
25 | Executing CI/CD pipeline for Front & Back End | Bala | 2022-06-15 | Completed
26 | Custom Domain and SSL | Megha/Bala/Swetha | 2022-06-16 | Completed
27 | Troubleshooting the Errors | Bala/Megha/Swetha | 2022-06-17 | Completed
28 | Application accessible to end users | Bala/Megha/Swetha | 2022-06-17 | Completed
29 | Stakeholder signoff | Megha/Swetha/Bala | 2022-06-16 | In Progress
Phase 4 : Break fix and Support
30 | Documentation and KT | Swetha/Bala | 2022-06-17 | Completed
31 | Application and environment monitoring | Swetha/Bala | 2022-06-17 | Completed

## Infra Architecture
Infrastructure Architecture Diagram | Legends
| S.No. | Explanation
| 1 | In browser the user search the app domain name and gets the static content from the CDN
| 2 | CDN will point to the App service and user gets the fron end page
| 3 | User signs in to the application through an Azure Active Directory B2C tenant (User within the AD only)
| 4 | User searches for the ticket details from the SQL DB
| 5 | Redis cache stores the frequently queried results
| 6 | When the same query has been queried next time, It will get the result from the Redis Cache
| 7 | When the user searches for the concerts, it will use the Azure Search service to the recommended concerts
| 8 | Web site stores the purchased ticket images in Blob Storage
| 9 | Azure search service gets the ticket information from the SQL BD
| 10 | User submits ticket orders and concert reviews, which are placed in the queue
| 11 | Azure Functions processes order payment and concert reviews
| 12 | Functions stores the generated ticket image in the Blob storage
| 13 | And also the functions stores the ticket details in the SQL DB as well
| 14 | Cognitive Services provides an analysis of the concert review to determine the sentiment (positive or negative)
| 15 | Application Insights provides performance metrics for monitoring the health of the web application

## Branching strategy for infra
Branching Strategy For Infrastructure

## Pipeline strategy for Infra
Pipeline Strategy for Infrastructure | Legends
| S.No. | Explanation
| 1 | Pull request will be created from feature to Dev
| 2 | Dev CI Pipeline triggers when a merge was done to Dev branch​
| 3 | Azure Blueprint task creates and publish the blueprint for Dev environment
| 4 | Pull request will be created from Dev to Main
| 5 | If the Reviewer approves the merge request merge will be done to Main branch
| 6 | If the Reviewer denies the merge request it will be denied
| 7 | Once a merge was done to Main branch the release pipeline will automatically triggers and wait for the Predeployment approval
| 8 | The admin has to approve the request
| 9 | If the admin approves the request release pipeline will start executing
| 10 | If the admin denies the request pipeline will start executing
| 11 | Azure Blueprint task assigns the blueprint values for the created blueprint
| 12 | Azure Appservice and the sql database will be created once the pipeline execution completes

## Control Flow Strategy for Infra
Control Flow Strategy for Infrastructure

## Branching Strategy Devops
Branching Strategy For DevOps

## Pipeline Architecture - Devops
Pipeline Strategy For DevOps - Front End App Service | Legends
| S.No. | Explanation
| 1 | Pull request will be created from feature to Dev
| 2 | Then again a pull request will be created to Main
| 3 | Once the merge was completed the Build Pipeline builds the artifact
| 4 | After Build pipeline was completed, the release pipeline automatically triggers and an admin must approve the request for the release pipeline
| 5 | If the admin approves the request, the release pipeline starts executing
| 6 | If the admin denies the request, the release pipeline ends
| 7 | Once the release pipeline execution was completed the artifact will be deployed in App Service
Pipeline Strategy For DevOps - Back End Functions | Legends
| S.No. | Explanation
| 1 | Pull request will be created from feature to Dev
| 2 | Then again a pull request will be created to Main
| 3 | Once the merge was completed the Build Pipeline builds the artifact
| 4 | After Build pipeline was completed, the release pipeline automatically triggers and an admin must approve the request for the release pipeline
| 5 | If the admin approves the request, the release pipeline starts executing
| 6 | If the admin denies the request, the release pipeline ends
| 7 | Once the release pipeline execution was completed the artifact will be deployed in Functions App

## DevOps Control Flow
Control Flow For DevOps - Front End App Service
Control Flow For DevOps - Back End Function App

## Cost Estimation
S.No. | Service Type | Region | No. of Instance | Description | Monthly cost in Rupees | 1 Weeks Cost
1 | Content Delivery Network | - | 1 | Zone 1: 0 GB, Zone 2: 2 GB, Zone 3: 0 GB, Zone 4: 0 GB, Zone 5: 0 GB, DSA: 2 GB | 47.41 | 11
2 | Traffic Manager | East US | 1 | 0.1 million DNS queries/mo, 1 Azure endpoint(s), 0 Fast Azure endpoint(s), 0 External endpoint(s), 0 Fast External endpoint(s), 0 million(s) of user measurements, 0 million(s) of data points processed. | 31.86 | 7.33
3 | App Service | East US | 1 | Free Tier; 1 F1 (0 Core(s), 1 GB RAM, 1 GB Storage) x 730 Hours; Windows OS | 0 | 0
4 | Storage Accounts - Queue | East US | 1 | Queue Storage, General Purpose V2, LRS Redundancy, 1 GB Capacity, 100 Queue Class 1 operations | 66.06 | 15.2
5 | Azure Functions | West US | 1 | Consumption tier, 128 MB memory, 100 milliseconds execution time, 0 executions/mo | 0 | 0
6 | Storage Accounts - (Functions and Image storage) | East US | 1 | Block Blob Storage, General Purpose V2, LRS Redundancy, Hot Access Tier, 1 GB Capacity - Pay as you go, 10 x 10,000 Write operations, 10 x 10,000 List and Create Container Operations, 10 x 10,000 Read operations, 1,00,000 Archive High Priority Read, 1 x 10,000 Other operations. 1,000 GB Data Retrieval, 1,000 GB Archive High Priority Retrieval, 1,000 GB Data Write | 82.38 | 19
8 | Azure Cognitive Search | East US | 1 | Free tier | 0 | 0
9 | Azure Cache for Redis | West US | 1 | Basic tier; 1 C0 instances, 14 Days | 574.33 | 124.8
10 | Azure SQL Database | East US | 1 | Single Database, LRS, DTU Purchase Model, Basic Tier, B: 5 DTUs, 2 GB included storage per DB, 1 Database(s) x 730 Hours, 0 GB Storage, 5 GB Long Term Retention | 380.82 | 85.45
11 | Private Endpoint | East US | 1 | Private endpoint: 1* 730 hrs, 5 GB data outbound processed, 5GB data inbound | 574.05 | 124.8
12 | Azure Monitor | East US | 1 | Log analytics: 0 GB Daily logs ingested; Application Insights: 0.2 GB Daily logs ingested, 3 months Data retention, 0 Multi-step Web Tests; 0 resources monitored X 1 metric time-series monitored per resource, 0 Log Alerts at 5 Minutes Frequency, 0 Additional events, 0 Additional emails, 0 Additional push notifications, 0 Additional web hooks (in millions) | 178.75 | 41.13
13 | Key Vault | East US | 1 | Vault: 10,000 operations, 10,000 advanced operations, 0 renewals, 0 protected keys, 0 advanced protected keys; Managed HSM Pools: 0 Standard B1 HSM Pool(s) x 730 Hours | 13.99 | 3.25
Total |  |  |  |  | 1949.65 | 431.96
NOTE:
The Above mentioned Cost estimation is based on the Assumption.

## Naming Conversion
S.No. | Services | Naming
1 | App service | Ava-Eus-Music-Concert-AppSvc
2 | App service - Plan | Ava-Eus-Music-Concert-Asp
3 | Functions app | Ava-Eus-Music-Concert-Func
4 | Functions app service - plan | ASP-AVAEUSADVANCEDUSECASEMUSICCONCE-ba40
5 | Azure active directory B2C | AVA B2C
6 | Application Insights | Ava-Eus-Music-Concert-AppInsights
7 | Redis Cache | Ava-Eus-Music-Concert-Redis-Cache
8 | Search Service | ava-eus-music-concert-search
9 | SQL Database | Ava-Eus-Music-Concert-S
10 | SQL Server | ava-eus-music-concert-sql-server
11 | Storage Account | Ava-Eus-Music-Concert-Sql-Db
12 | Content Delivery Network | Ava-Eus-Music-Concert-CDN
13 | Key Vault | Ava-Eus-Music-Concert-KV
14 | Managed Identity | Adv-uscase-MI
15 | Virtual Network | Ava-Eus-Music-Concert-Vnet
16 | Private Endpoint | Ava-Eus-Music-Concert-PvtEndPnt
17 | Regular Network Interface | Ava-Eus-Music-Concert-PvtEndPnt-nic
18 | CDN endpoint | Musicconcert-CDN (Ava-Eus-Music-Concert-CDN/Musicconcert-CDN)

## SOP links
S.No. | Topic | Links
1 | SOP - Infrastructure Pipeline Setup using Blueprint | Infrastructure Pipeline Setup using Blueprint
2 | SOP - Application Pipeline Setup | Application DevOps Pipeline Setup
3 | SOP - App Service creation | App Service Creation
4 | SOP - Application Insights Creation | Applicatioin Insights creation
5 | SOP - App Registration | App Registration Creation
6 | SOP - Azure B2C Tenant Creation | B2C Tenant Creation
7 | SOP - CDN Creation | CDN Creation
8 | SOP - Key Vault creation | Key Vault Creation
9 | SOP - Search Service Creation | Search Service Creation
10 | SOP - Redis Creation | Redis Creation
11 | SOP - Register CDN Service Principle | Register CDN Service Principle
12 | SOP - Usecase Implementation | Usecase Implementation
13 | Demo Video | Advanced Use case Demo Video.mkv

## Escalation Access Matrix
S.No. | Client | Escalation Level | Designation | Resource | E-mail | Contact Details
1 | SAP Technologies | Level - 4 | Engagement Manager | Lakshmi Narayanan SP | lakshminarayanan.sp@avasoft.com | 7892405967
|  | Level - 3 | Service Delivery Manager | Meghavardhini K | meghavardhini.k@avasoft.com | 8508308867
|  | Level - 2 | Technical Lead | Swetha Dhayalan | swetha.d@avasoft.com | 7550165231
|  | Level - 1 | Engineer | Balakrishnan Padmanaban | balakrishnan.p@avasoft.com | 6379986058

## Understanding
S.No. | Components | Description | Reffered Links | Screenshots
1 | Azure App Service | App Service is a Platform as a Service (PaaS) offering from Microsoft. We use it to host web applications, REST API's and backend services for mobile applications. | https://docs.microsoft.com/en-in/azure/app-service/overview
2 | Azure Functions | Azure Function is a serverless compute service that enables user to run event-triggered code without having to provision or manage infrastructure. Being as a trigger-based service, it runs a script or piece of code in response to a variety of events. | https://docs.microsoft.com/en-us/azure/azure-functions/
3 | Azure Active Directory B2C | •Azure Active Directory B2C provides business-to-customer identity as a service. Your customers use their preferred social, enterprise, or local account identities to get single sign-on access to your applications and APIs. •Azure AD B2C is a customer identity access management (CIAM) solution capable of supporting millions of users and billions of authentications per day. •It takes care of the scaling and safety of the authentication platform, monitoring, and automatically handling threats like denial-of-service, password spray, or brute force attacks. •Azure AD B2C is a white-label authentication solution. | https://docs.microsoft.com/en-us/azure/active-directory-b2c/faq?WT.mc_id=Portal-Microsoft_AAD_B2CAdmin&tabs=app-reg-ga#why-cant-i-access-the-azure-ad-b2c-extension-in-the-azure-portal
4 | Redis cache | •Redis is an open source, in-memory data store used by millions of developers as a database, cache, streaming engine, and message broker. •Azure Cache for Redis provides an in-memory data store based on the Redis software. Redis improves the performance and scalability of an application that uses backend data stores heavily. | https://docs.microsoft.com/en-us/azure/azure-cache-for-redis/cache-overview
5 | Azure Cognitive Services | •Azure Cognitive Services are cloud-based artificial intelligence (AI) services that help you build cognitive intelligence into your applications. •They are available as REST APIs, client library SDKs, and user interfaces. You can add cognitive features to your applications without having AI or data science skills. | https://docs.microsoft.com/en-in/azure/cognitive-services/what-are-cognitive-services

## Business Understanding
Business | Understanding
Relecloud Concerts | • Online concert ticketing platform • In this application, customers can search for their favorite concerts • Purchase tickets safely • View their tickets • Customers can view upcoming events • Customers can give their feedback which will help to improve the application and as well as the concert • The application is going to deploy in a serverless so the backend does not need to run always and it saves cost

## Moving Components
S.No. | Moving Components | Usage
1 | App service | hosts web applications allowing autoscale and high availability without having to manage infrastructure
2 | Functions app | are serverless compute options that allow applications to run on-demand without having to manage infrastructure
3 | Azure active directory B2C | is an identity management service that enables customization and control over how customers sign up, sign in, and manage their profiles in an application
4 | Application Insights | is designed to help you continuously improve performance and usability by automatically detecting performance anomalies through built-in analytics tools to help understand what users do with an app
5 | Redis Cache | improves the performance and scalability of systems that rely heavily on back-end data stores by temporarily copying frequently accessed data to fast storage located close to the application
6 | Search Service | is a search-as-a-service cloud solution that provides a rich search experience over private, heterogeneous content in web, mobile, and enterprise applications
7 | SQL Database | are optimized to store large amounts of unstructured data, such as text or binary data
8 | Storage Account - Queue | stores large numbers of queue messages that can be accessed by an application
9 | Storage Account - Blob | are optimized to store large amounts of unstructured data, such as text or binary data
10 | Content Delivery Network | delivers static, cached content from locations close to users to reduce latency
11 | Cognitive Services | uses machine learning APIs and enables developers to easily add intelligent features – such as emotion and video detection; facial, speech, and vision recognition; and speech and language understanding – into applications
12 | Traffic Manager | This service allows you to distribute traffic to your public facing applications across the global Azure regions and controls the distribution of user traffic for service endpoints in different Azure regions.
13 | Key Vault | Used to store the SSL certificate

## Doc Plan
S.No | Tasks / Work items | Resource | ETA | Status | Review Status
1 | App service creation documentation | Bala | 2022-06-20 | Completed
2 | Custom domain creation and DNS record entry documentation | Bala | 2022-06-20 | Completed
3 | Configure the custom domain in app service | Swetha | 2022-06-20 | Completed
4 | Setup Azure CDN | Swetha | 2022-06-20 | Completed
5 | SQL DB creation and configuration | Bala | 2022-06-21 | Completed
6 | Redis cache creation and configuration | Swetha | 2022-06-21 | Completed
7 | Azure search service creation and configuration | Bala | 2022-06-21 | Completed
8 | Azure AD B2C tenant creation and policy configuration | Bala | 2022-06-21 | Completed
9 | Functions creation and configuration | Bala | 2022-06-22 | Completed
10 | Storage account configuration (Blob and Queue) | Swetha | 2022-06-21 | Completed
11 | Infra pipeline configuration | Swetha | 2022-06-23 | Completed
12 | Deployment pipeline configuration | Swetha | 2022-06-23 | Completed
13 | Demo video | Bala | 2022-06-21 | Completed

## Azure AD B2C Tenant pricing
Billing model for Azure Active Directory B2C ¦ Microsoft Docs
Pricing - Active Directory External Identities ¦ Microsoft Azure
Topics | Understanding | Azure AD B2C Tenant Pricing Model
AD B2C Pricing features | • The Azure AD B2C only has two types of licenses which are Premium License (P1 and P2) | S.No. | Licenses available | Pricing
| • In both P1 and P2 licenses, for 50,000 users it will be free for every billing period | 1 | Premium P1 | 50,000/users - free then ₹0.25/user
| • After that, they will charge Rs. 0.25/active users | 2 | Premium P2 | 50,000/users - free then ₹1.26/user
To delete the Tenant | Clean up resources and delete a tenant - Azure Active Directory B2C ¦ Microsoft Docs

## Other Ref
Application settings Vs Connecting Strings in App service | Azure App Service connection strings and ASP.NET Core - How?! ¦ Mickaël Derriey's blog (mderriey.com)
Load-balancing options - Azure Architecture Center ¦ Microsoft Docs
How Azure search service connects to DB torugh code | Azure SQL indexer - Azure Cognitive Search ¦ Microsoft Docs
How Application insights connect through code | Add Application Insight In Existing ASP.NET Web Application (c-sharpcorner.com)